## Hoja1
WORK PLAN NIA WG
From December 2015-August 2016
|  |  | RESPONSIBLE | DELIVERABLES | DUE DATE
Diagnosis | Task 1: GI index building | 1.1 Research, documentation and external validation |  |  | April 2016
|  | Research and documentation about work already done in this sense by other organisations or institutions | NIA Group → Secretariat
1.2 Index building
|  | - Identify and score the parameters which affect BP in production systems and index building | TG1-Spain
|  | - Identify and score the parameters which affect BP in dissemination, funding and policy models and index building | TG2-Mexico
|  | - Identify and score the parameters which affect BP in structures of the organisations and VGI role and index building | TG3-Singapore
|  | 1.3 Internal report | NIA WG | X
| Task 2: Assessment | 2.1 Assessment |  |  | Jun 2016
Analyse and interpret the available information to have an assessment of the issues related to each TG, based on the previuos indicators
|  | - Draft report on production systems assessment | TG1-Spain
|  | - Draft report on dissemination, funding and policy models assessment | TG2-Mexico
|  | - Draft report on organizational structures and VGI role assessment | TG3-Singapore
|  | 2.2 Circulation NIA WG | NIA WG
|  | 2.3 Validation of results by external organisations | NIA WG → Secretariat
|  | 2.4 Final report: Trends in NIA | NIA WG → Secretariat | X
To be presented in NY August 2016
| Task 3 | Case studies |  |  | To be decided by NIA and Secretariat
Selection of case studies on each topic based on the results of assessment
Identification of Best Practices | Task 4 | First conclusions of Best Practices
Identification of Best Practices and production of a joint report with the contribution of each TG with the first conclusions
Best practices on Production systems
Best practices on Dissemination, funding and policy models
Best practices on Organizational structures and VGI role
Consultation among groups and NIA WG | Task 5 | Distribution to five Regions for revision
Circulation of the report for consultation
Submission of Reports and Technical Papers | Task 6 | Report on Best Practices
Final report
TO BE DONE